## General
Project 3 - Abalone
Python Backend
Data cleansing
| Y | Load data from CSV
| Y | Unscale data
| Y | Add Age column
| Y | Label encode "Sex" column
| Y | Binary encode "Sex" column
| Y | Reorganize columns
Load data to MongoDB
| Y | Create dictionary of JSONs
| Y | Create DB in MongoDB
| Y | Insert records into collection
Flask App
| Y | Route to provide website all abalone data
| N | Route to receive user data and return model prediction
Either load a previously-saved model, or
Load data and create model
Website
Home page
| N | Intro
| N | User input abalone data to get a prediction
Data page
| N | Call Flask GET route to retrieve all abalone data
| N | Use DataTables/jQuery to display data table
About page
| N | Team info
| N | Project tech stack / architecture diagram
Voila
| N | Provide link to notebook analysis
PowerPoint Presentation
| N | Intro
| N | Summary / Descriptive stats
| N | ML Models
| N | NN Models
| N | Conclusions
Summary / Descriptive Stats
via Tableau
| Y | Count of records by "Sex"
| N | Count of records by "Rings"
via Jupyter Notebook
| Y | Dataframe.describe()
| Y | Count of records by "Sex"
| N | Count of records by "Rings"
| Y | Histogram of Rings column
| Y | Scatter matrix
| N | Correlation matrix like Project 1
ML Models
Linear Regression
| Y | LinearRegression
| Y | LASSO
| Y | Ridge
| Y | ElasticNet
Classification Models
| Y | LogisticRegression
| Y | RandomForest
| Y | KNN
| Y | SVM
AutoML
NN Models

## Linear-LinearRegression
|  |  |  | Scale w/ StandardScaler | Output: MSE = 0.46242287094296114 R2 = 0.5314335652471704
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE = 0.006148368504522266 R2 = 0.5314335652471704
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE = 0.5355912119494953 R2 = 0.5314335652471703
|  |  |  | Scale w/ PowerTransformer | Output: MSE = 0.40785526390006877 R2 = 0.5948452977921383
with all Rings data
|  |  |  | Scale w/ StandardScaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ Min-Max Scaler | N/A - Cannot stratify all Rings data
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ PowerTransformer | N/A - Cannot stratify all Rings data
with Sex-LabelEncoded
|  |  |  | Scale w/ StandardScaler | Output: MSE = 0.5507882657717592 R2 = 0.4454929364949701
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE = 0.011415150121607695 R2 = 0.4454929364949698
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE = 0.2853787530401922 R2 = 0.44549293649497024
|  |  |  | Scale w/ PowerTransformer | Output: MSE = 0.5655118524376348 R2 = 0.46818880998822765
with Rings in bins
|  |  |  | Scale w/ StandardScaler | Output: MSE = 0.6120365656891271 R2 = 0.3804995136121635
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE = 0.012708636721813271 R2 = 0.3804995136121635
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE = 0.3177159180453317 R2 = 0.3804995136121635
|  |  |  | Scale w/ PowerTransformer | Output: MSE = 0.5817333662597395 R2 = 0.41382288773720055
LinearRegression
|  |  |  | Scale w/ StandardScaler | Output: MSE = 0.4485686704789443 R2 = 0.5454718270324015
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE = 0.00596362021056461 R2 = 0.5455132108251372
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE = 0.5194840620832833 R2 = 0.5455250395254155
|  |  |  | Scale w/ PowerTransformer | Output: MSE = 0.39464120768549266 R2 = 0.6079718588162135
with all Rings data
|  |  |  | Scale w/ StandardScaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ Min-Max Scaler | N/A - Cannot stratify all Rings data
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ PowerTransformer | N/A - Cannot stratify all Rings data
with Sex-Binary Encoded
|  |  |  | Scale w/ StandardScaler | Output: MSE = 0.5475436235533739 R2 = 0.44875948580338765
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE = 0.011348084414974927 R2 = 0.4487507480568548
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE = 0.28371140762949676 R2 = 0.4487326829641235
|  |  |  | Scale w/ PowerTransformer | Output: MSE = 0.5633661336434109 R2 = 0.47020665852750776
with Rings in bins
|  |  |  | Scale w/ StandardScaler | Output: MSE = 0.6072060048580934 R2 = 0.3853889841962975
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE = 0.012608367388328299 R2 = 0.3853872842065583
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE = 0.31497437782835164 R2 = 0.3858451239558941
|  |  |  | Scale w/ PowerTransformer | Output: MSE = 0.5789893036434766 R2 = 0.4165879117044713

## Linear-LASSO
|  |  |  | Scale w/ StandardScaler | Output: MSE R2
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE R2
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE R2
|  |  |  | Scale w/ PowerTransformer | Output: MSE R2
with all Rings data
|  |  |  | Scale w/ StandardScaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ Min-Max Scaler | N/A - Cannot stratify all Rings data
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ PowerTransformer | N/A - Cannot stratify all Rings data
with Sex-LabelEncoded
|  |  |  | Scale w/ StandardScaler | Output: MSE R2
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE R2
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE R2
|  |  |  | Scale w/ PowerTransformer | Output: MSE R2
with Rings in bins
|  |  |  | Scale w/ StandardScaler | Output: MSE R2
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE R2
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE R2
|  |  |  | Scale w/ PowerTransformer | Output: MSE R2
LASSO
|  |  |  | Scale w/ StandardScaler | Output: MSE R2
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE R2
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE R2
|  |  |  | Scale w/ PowerTransformer | Output: MSE R2
with all Rings data
|  |  |  | Scale w/ StandardScaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ Min-Max Scaler | N/A - Cannot stratify all Rings data
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ PowerTransformer | N/A - Cannot stratify all Rings data
with Sex-Binary Encoded
|  |  |  | Scale w/ StandardScaler | Output: MSE R2
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE R2
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE R2
|  |  |  | Scale w/ PowerTransformer | Output: MSE R2
with Rings in bins
|  |  |  | Scale w/ StandardScaler | Output: MSE R2
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE R2
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE R2
|  |  |  | Scale w/ PowerTransformer | Output: MSE R2

## Linear-Ridge
|  |  |  | Scale w/ StandardScaler | Output: MSE R2
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE R2
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE R2
|  |  |  | Scale w/ PowerTransformer | Output: MSE R2
with all Rings data
|  |  |  | Scale w/ StandardScaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ Min-Max Scaler | N/A - Cannot stratify all Rings data
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ PowerTransformer | N/A - Cannot stratify all Rings data
with Sex-LabelEncoded
|  |  |  | Scale w/ StandardScaler | Output: MSE R2
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE R2
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE R2
|  |  |  | Scale w/ PowerTransformer | Output: MSE R2
with Rings in bins
|  |  |  | Scale w/ StandardScaler | Output: MSE R2
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE R2
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE R2
|  |  |  | Scale w/ PowerTransformer | Output: MSE R2
Ridge
|  |  |  | Scale w/ StandardScaler | Output: MSE R2
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE R2
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE R2
|  |  |  | Scale w/ PowerTransformer | Output: MSE R2
with all Rings data
|  |  |  | Scale w/ StandardScaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ Min-Max Scaler | N/A - Cannot stratify all Rings data
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ PowerTransformer | N/A - Cannot stratify all Rings data
with Sex-Binary Encoded
|  |  |  | Scale w/ StandardScaler | Output: MSE R2
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE R2
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE R2
|  |  |  | Scale w/ PowerTransformer | Output: MSE R2
with Rings in bins
|  |  |  | Scale w/ StandardScaler | Output: MSE R2
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE R2
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE R2
|  |  |  | Scale w/ PowerTransformer | Output: MSE R2

## Linear-ElasticNet
|  |  |  | Scale w/ StandardScaler | Output: MSE R2
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE R2
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE R2
|  |  |  | Scale w/ PowerTransformer | Output: MSE R2
with all Rings data
|  |  |  | Scale w/ StandardScaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ Min-Max Scaler | N/A - Cannot stratify all Rings data
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ PowerTransformer | N/A - Cannot stratify all Rings data
with Sex-LabelEncoded
|  |  |  | Scale w/ StandardScaler | Output: MSE R2
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE R2
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE R2
|  |  |  | Scale w/ PowerTransformer | Output: MSE R2
with Rings in bins
|  |  |  | Scale w/ StandardScaler | Output: MSE R2
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE R2
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE R2
|  |  |  | Scale w/ PowerTransformer | Output: MSE R2
ElasticNet
|  |  |  | Scale w/ StandardScaler | Output: MSE R2
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE R2
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE R2
|  |  |  | Scale w/ PowerTransformer | Output: MSE R2
with all Rings data
|  |  |  | Scale w/ StandardScaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ Min-Max Scaler | N/A - Cannot stratify all Rings data
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ PowerTransformer | N/A - Cannot stratify all Rings data
with Sex-Binary Encoded
|  |  |  | Scale w/ StandardScaler | Output: MSE R2
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE R2
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE R2
|  |  |  | Scale w/ PowerTransformer | Output: MSE R2
with Rings in bins
|  |  |  | Scale w/ StandardScaler | Output: MSE R2
|  |  |  | Scale w/ Min-Max Scaler | Output: MSE R2
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | Output: MSE R2
|  |  |  | Scale w/ PowerTransformer | Output: MSE R2

## Classification-LogisticReg
|  |  |  | Scale w/ StandardScaler | Output: Training data score = 0.2777777777777778 Testing Data Score = 0.27751196172248804
|  |  |  | Scale w/ Min-Max Scaler | Output: Training data score = 0.2547892720306513 Testing Data Score 0.2679425837320574
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: Training data score = 0.2771392081736909 Testing Data Score = 0.2822966507177033
|  |  |  | Scale w/ PowerTransformer | Output: Training data score = 0.28160919540229884 Testing Data Score = 0.2698564593301435
with all Rings data
|  |  |  | Scale w/ StandardScaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ Min-Max Scaler | N/A - Cannot stratify all Rings data
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ PowerTransformer | N/A - Cannot stratify all Rings data
with Sex-LabelEncoded
|  |  |  | Scale w/ StandardScaler | Output: Training data score = 0.7049808429118773 Testing Data Score = 0.6832535885167464
|  |  |  | Scale w/ Min-Max Scaler | Output: Training data score = 0.688058748403576 Testing Data Score = 0.6708133971291866
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: Training data score = 0.7059386973180076 Testing Data Score = 0.6813397129186602
|  |  |  | Scale w/ PowerTransformer | Output: Training data score = 0.7088122605363985 Testing Data Score = 0.6889952153110048
with Rings in bins
|  |  |  | Scale w/ StandardScaler | Output: Training data score = 0.7021072796934866 Testing Data Score = 0.6851674641148325
|  |  |  | Scale w/ Min-Max Scaler | Output: Training data score = 0.6848659003831418 Testing Data Score = 0.6794258373205742
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | Output: Training data score = 0.6995530012771393 Testing Data Score = 0.6851674641148325
|  |  |  | Scale w/ PowerTransformer | Output: Training data score = 0.7081736909323116 Testing Data Score = 0.6889952153110048
LogisticRegression
|  |  |  | Scale w/ StandardScaler | Output: Training data score = 0.28001277139208175 Testing Data Score = 0.2822966507177033
|  |  |  | Scale w/ Min-Max Scaler | Output: Training data score = 0.25351213282247764 Testing Data Score = 0.2602870813397129
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: Training data score = 0.2768199233716475 Testing Data Score = 0.28038277511961723
|  |  |  | Scale w/ PowerTransformer | Output: Training data score = 0.2835249042145594 Testing Data Score = 0.2755980861244019
with all Rings data
|  |  |  | Scale w/ StandardScaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ Min-Max Scaler | N/A - Cannot stratify all Rings data
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ PowerTransformer | N/A - Cannot stratify all Rings data
with Sex-Binary Encoded
|  |  |  | Scale w/ StandardScaler | Output: Training data score = 0.7011494252873564 Testing Data Score = 0.6880382775119617
|  |  |  | Scale w/ Min-Max Scaler | Output: Training data score = 0.6874201787994891 Testing Data Score = 0.6727272727272727
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: Training data score = 0.7021072796934866 Testing Data Score = 0.6842105263157895
|  |  |  | Scale w/ PowerTransformer | Output: Training data score = 0.7110472541507025 Testing Data Score = 0.691866028708134
with Rings in bins
|  |  |  | Scale w/ StandardScaler | Output: Training data score = 0.7027458492975734 Testing Data Score = 0.6822966507177034
|  |  |  | Scale w/ Min-Max Scaler | Output: Training data score = 0.6839080459770115 Testing Data Score = 0.6803827751196172
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | Output: Training data score = 0.7005108556832694 Testing Data Score = 0.6794258373205742
|  |  |  | Scale w/ PowerTransformer | Output: Training data score = 0.7091315453384419 Testing Data Score = 0.6832535885167464

## Classification-RandomForest
|  |  | Train-Test-Split without stratify option | Output: Training data score = 1.0 Testing Data Score = 0.2507177033492823
with all Rings data
|  |  | Train-Test-Split with stratify option | N/A - Cannot stratify all Rings data
with Sex-LabelEncoded
|  |  | Train-Test-Split without stratify option | Output: Training data score = 1.0 Testing Data Score = 0.6947368421052632
with Rings in bins
|  |  | Train-Test-Split with stratify option | Output: Training data score = 1.0 Testing Data Score = 0.692822966507177
RandomForest
|  |  | Train-Test-Split without stratify option | Output: Training data score = 1.0 Testing Data Score = 0.25645933014354066
with all Rings data
|  |  | Train-Test-Split with stratify option | N/A - Cannot stratify all Rings data
with Sex-Binary Encoded
|  |  | Train-Test-Split without stratify option | Output: Training data score = 1.0 Testing Data Score = 0.6976076555023923
with Rings in bins
|  |  | Train-Test-Split with stratify option | Output: Training data score = 1.0 Testing Data Score = 0.6956937799043063

## Classification-KNN
|  |  |  | Scale w/ StandardScaler | Output: k: 17, Train/Test Score: 0.345/0.272
|  |  |  | Scale w/ Min-Max Scaler | Output: k: 17, Train/Test Score: 0.349/0.255
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: k: 17, Train/Test Score: 0.345/0.284
|  |  |  | Scale w/ PowerTransformer | Output: k: 13, Train/Test Score: 0.352/0.258
with all Rings data
|  |  |  | Scale w/ StandardScaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ Min-Max Scaler | N/A - Cannot stratify all Rings data
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ PowerTransformer | N/A - Cannot stratify all Rings data
with Sex-LabelEncoded
|  |  |  | Scale w/ StandardScaler | Output: k: 19, Train/Test Score: 0.723/0.700
|  |  |  | Scale w/ Min-Max Scaler | Output: k: 15, Train/Test Score: 0.715/0.701
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: k: 15, Train/Test Score: 0.727/0.695
|  |  |  | Scale w/ PowerTransformer | Output: k: 19, Train/Test Score: 0.722/0.697
with Rings in bins
|  |  |  | Scale w/ StandardScaler | Output: k: 19, Train/Test Score: 0.716/0.704
|  |  |  | Scale w/ Min-Max Scaler | Output: k: 19, Train/Test Score: 0.722/0.703
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | Output: k: 19, Train/Test Score: 0.717/0.702
|  |  |  | Scale w/ PowerTransformer | Output: k: 19, Train/Test Score: 0.723/0.700
KNN
|  |  |  | Scale w/ StandardScaler | Output: k: 17, Train/Test Score: 0.343/0.273
|  |  |  | Scale w/ Min-Max Scaler | Output: k: 17, Train/Test Score: 0.348/0.255
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: k: 17, Train/Test Score: 0.346/0.283
|  |  |  | Scale w/ PowerTransformer | Output: k: 19, Train/Test Score: 0.331/0.259
with all Rings data
|  |  |  | Scale w/ StandardScaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ Min-Max Scaler | N/A - Cannot stratify all Rings data
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ PowerTransformer | N/A - Cannot stratify all Rings data
with Sex-Binary Encoded
|  |  |  | Scale w/ StandardScaler | Output: k: 19, Train/Test Score: 0.722/0.700
|  |  |  | Scale w/ Min-Max Scaler | Output: k: 15, Train/Test Score: 0.715/0.701
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: k: 19, Train/Test Score: 0.716/0.699
|  |  |  | Scale w/ PowerTransformer | Output: k: 19, Train/Test Score: 0.721/0.697
with Rings in bins
|  |  |  | Scale w/ StandardScaler | Output: k: 19, Train/Test Score: 0.716/0.704
|  |  |  | Scale w/ Min-Max Scaler | Output: k: 19, Train/Test Score: 0.722/0.703
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | Output: k: 19, Train/Test Score: 0.718/0.703
|  |  |  | Scale w/ PowerTransformer | Output: k: 19, Train/Test Score: 0.723/0.700

## Classification-SVM
|  |  |  | Scale w/ StandardScaler | Output: Training Acc: 0.268 Test Acc: 0.285
|  |  |  | Scale w/ Min-Max Scaler | Output: Training Acc: 0.255 Test Acc: 0.262
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: Training Acc: 0.267 Test Acc: 0.278
|  |  |  | Scale w/ PowerTransformer | Output: Training Acc: 0.269 Test Acc: 0.276
with all Rings data
|  |  |  | Scale w/ StandardScaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ Min-Max Scaler | N/A - Cannot stratify all Rings data
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ PowerTransformer | N/A - Cannot stratify all Rings data
with Sex-LabelEncoded
|  |  |  | Scale w/ StandardScaler | Output: Training Acc: 0.699 Test Acc: 0.699
|  |  |  | Scale w/ Min-Max Scaler | Output: Training Acc: 0.688 Test Acc: 0.687
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: Training Acc: 0.701 Test Acc: 0.700
|  |  |  | Scale w/ PowerTransformer | Output: Training Acc: 0.706 Test Acc: 0.706
with Rings in bins
|  |  |  | Scale w/ StandardScaler | Output: Training Acc: 0.702 Test Acc: 0.694
|  |  |  | Scale w/ Min-Max Scaler | Output: Training Acc: 0.688 Test Acc: 0.684
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | Output: Training Acc: 0.701 Test Acc: 0.692
|  |  |  | Scale w/ PowerTransformer | Output: Training Acc: 0.711 Test Acc: 0.693
SVM
|  |  |  | Scale w/ StandardScaler | Output: Training Acc: 0.267 Test Acc: 0.280
|  |  |  | Scale w/ Min-Max Scaler | Output: Training Acc: 0.250 Test Acc: 0.257
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: Training Acc: 0.266 Test Acc: 0.276
|  |  |  | Scale w/ PowerTransformer | Output: Training Acc: 0.270 Test Acc: 0.273
with all Rings data
|  |  |  | Scale w/ StandardScaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ Min-Max Scaler | N/A - Cannot stratify all Rings data
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | N/A - Cannot stratify all Rings data
|  |  |  | Scale w/ PowerTransformer | N/A - Cannot stratify all Rings data
with Sex-Binary Encoded
|  |  |  | Scale w/ StandardScaler | Output: Training Acc: 0.700 Test Acc: 0.699
|  |  |  | Scale w/ Min-Max Scaler | Output: Training Acc: 0.688 Test Acc: 0.687
Train-Test-Split without stratify option
|  |  |  | Scale w/ Robust Scaler | Output: Training Acc: 0.699 Test Acc: 0.698
|  |  |  | Scale w/ PowerTransformer | Output: Training Acc: 0.708 Test Acc: 0.707
with Rings in bins
|  |  |  | Scale w/ StandardScaler | Output: Training Acc: 0.703 Test Acc: 0.694
|  |  |  | Scale w/ Min-Max Scaler | Output: Training Acc: 0.690 Test Acc: 0.682
Train-Test-Split with stratify option
|  |  |  | Scale w/ Robust Scaler | Output: Training Acc: 0.701 Test Acc: 0.693
|  |  |  | Scale w/ PowerTransformer | Output: Training Acc: 0.714 Test Acc: 0.694